## Slide 1
BIANNUAL PROJECT REPORT
April 1, 2024 – September 30, 2024

## Slide 2: Coast Community College District Program Summary
Closed Projects
CCC College Center Restroom Renovation
CCC Energy Efficiency Projects
CCC Le-Jao Student Resource Center
CCC GG Center Solar P/V Carport System
CCC Newport Beach Student Support Center
CCC Student Services Center
GWC Campus Safety/Community Education Building & Campus Entry
GWC Elevator Repairs/Replacement
GWC Rehabilitation Center Remodel
GWC Campus-wide Wayfinding/Signage
GWC Math & Science Improvements
GWC MDF/Communications Relocation
GWC Technology Projects
GWC Security & Access Infrastructure
GWC Criminal Justice Training Center
Closed Projects (cont.)
GWC Energy Efficiency Upgrades
GWC Student Services Center
GWC Math/Science Building
GWC Classroom Improvement Projects
OCC IDC Phase I (Business, Math, Computing Center)
OCC Clark Center
OCC Energy Efficiency Projects
OCC Planetarium
OCC Solar PV/Adams Parking Lot Improvements
OCC Recycling Center
OCC Legacy Hall
OCC Watson Hall Renovation
OCC Technology Projects
OCC Securitization Fund
OCC Sustainable Landscape Improvements
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 2

## Slide 3: Coast Community College District Program Summary
Projects In Construction
OCC Chemistry
GWC General Education Demolition & Native Gardens Expansion
Other Ongoing Projects
CCC Technology Projects
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 3
Financial Closing
GWC Language Arts Complex
Closed Projects (cont.)
OCC Student Union Complex
OCC Adaptive PE, Gym & Pool
OCC Adams Lot Re-Paving
OCC Watson Hall Improvements
OCC Language Arts/Social Sciences Building
OCC Maritime Academy Expansion
DIST Technology Projects
State Funded Project Proposals
GWC Physical Education Rec (Gym) Replacement
OCC Skills Center Renovation/Replacement
Future Projects
CCC Le-Jao Parking Expansion
GWC Administration Demolition
OCC Social Sciences and Existing Chemistry Demolition
In Design
GWC Fine Arts Renovation

## Slide 4: Coast Community College District Split Budget Summary
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 4
Project | Total Budget | Non-Measure M | Measure M
CCC EE – GG Ctr. Boiler | $1,270,525 | $512,011 | $758,514
GWC Language Arts Complex | $54,675,848 | $19,670,543 | $35,005,305
GWC Criminal Justice Training Center | $27,765,999 | $900,000 | $26,865,999
GWC EE – Exterior Lighting Retrofit | $513,409 | $505,914 | $7,495
GWC EE – Interior Lighting Retrofit | $432,088 | $422,013 | $10,075
GWC Gen Ed Demolition & Nature Park Expansion | $4,500,000 | $3,000,000 | $1,500,000
GWC Fine Arts Renovation | $35,261,219 | $16,004,000 | $19,257,219
OCC Language/Social Science Building | $74,941,728 | $30,353,000 | $44,588,728
OCC EE – Exterior Lighting Retrofit | $1,369,092 | $679,189 | $689,903
OCC SL – Landscape Improvements | $1,008,000 | $125,000 | $883,000
OCC Adams Lot Repaving | $1,600,000 | $100,000 | $1,500,000
OCC Chemistry | $44,487,553 | $20,194,000 | $24,293,553
OCC EE – Campus Sub-metering Project | $1,311,306 | $634,000 | $677,306
TOTALS | $249,136,767 | $93,099,670 | $156,037,097

## Slide 5: Coastline College Technology Projects
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 5
Project | Budget | Biannual Expenses | Total Expended | Balance Remaining
TECH – Classroom Technology Upgrades | $1,900,015 | $0 | $1,400,015 | $500,000
TECH – IT Infrastructure Improvements | $1,197,065 | $0 | $1,197,065 | $0
TECH – Student Kiosks, Wayfinding Signages | $1,286,925 | $0 | $286,925 | $1,000,000
Totals | $4,384,005 | $0 | $2,884,005 | $1,500,000
TOTAL ALLOCATION: $4,384,005

## Slide 6: Golden West College Language Arts Complex
Current Phase: Financial Closing
Architect: HMC Architects Contractor: Multi-Prime
Construction Manager: Sundt Construction
Construction of a new three-story 65,500 square foot instructional facility to replace 60 year old social sciences classrooms and 50 year old literature and languages building

## Slide 7: Golden West College Language Arts Complex

## Slide 8: Golden West College Language Arts Complex
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 8
 | Budget | Biannual Expenses | Total Expended | Balance Remaining
Construction | $25,517,672 | $2,317,964 | $22,514,094 | $3,003,578
Soft Cost | $5,609,285 | $33,847 | $5,600,191 | $9,094
FFE/IT | $2,898,348 | ($28,566) | $2,811,323 | $87,025
Contingency | $980,000 |  |  | $980,000
TOTAL | $35,005,305 | $2,323,245 | $30,925,608 | $4,079,697
 | Start
Design | August 2018
Plan Review | August 2019
Bidding | November 2020
Construction | January 2021
Project Completion | May 2023
Closeout | August 2023
BUDGET
SCHEDULE
Status Update: Project is completed. Final DSA closeout nearing completion.
*The Language Arts Complex is a 50/50 state funded project. Total project funding is captured in the split budget summary slide.

## Slide 9: Golden West College General Education Demolition and Nature Park Expansion
Current Phase: In Construction Architect: HMC Architects Contractor: Multi-Prime
Construction Manager: N/A
Demolition of the existing Golden West College General Education Building and New Site Work Improvements to expand access and usage of the existing Nature Garden.

## Slide 10: Golden West College General Education Demolition and Nature Park Expansion

## Slide 11: Golden West College General Education Demolition and Nature Park Expansion
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 11
 | Budget | Biannual Expenses | Total Expended | Balance Remaining
Construction | $1,000,000 | $536,527 | $1,761,697 | ($761,697)
Soft Cost | $250,000 | $28,786 | $37,803 | $212,197
FFE/IT | $0 | $0 | $0 | $0
Contingency | $250,000 |  |  | $250,000
TOTAL | $1,500,000 | $565,313 | $1,799,500 | ($299,500)
 | Start
Design | January 2023
Plan Review | May 2023
Bidding | June 2023
Construction | August 2023
Project Completion | October 2024
Closeout | November 2024
BUDGET
SCHEDULE
Status Update: Site landscaping and electrical work ongoing.
*General Education Demolition and Nature Park Expansion is only partially funded using Measure M. Total project funding is captured in the split budget summary slide.

## Slide 12: Golden West College Fine Arts Renovation
Current Phase: In Design Architect: Tbp Architecture Contractor: Multi-Prime
Construction Manager: N/A
The Fine Arts Renovation project at Golden West College will do a full gut and reconfiguration of one of the two wings of the existing Fine Arts Building. The other smaller wing will be demolished upon completion of the project.

## Slide 13: Golden West College Fine Arts Renovation

## Slide 14: Golden West College Fine Arts Renovation
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 14
 | Budget | Biannual Expenses | Total Expended | Balance Remaining
Construction | $12,685,720 | $0 | $0 | $12,685,720
Soft Cost | $2,500,000 | $1,005,561 | $1,398,155 | $1,101,845
FFE/IT | $2,344,000 | $0 | $0 | $2,344,000
Contingency | $1,727,499 |  |  | $1,727,499
TOTAL | $19,257,219 | $1,005,561 | $1,398,155 | $17,859,064
 | Start
Design | December 2023
Plan Review | February 2024
Bidding | March 2025
Construction | May 2025
Project Completion | March 2027
Closeout | July 2027
BUDGET
SCHEDULE
Status Update: Preliminary plans completed. DSA Plan review scheduled. Geotechnical engineer has completed boring samples and provided analysis.
*The Fine Arts Renovation is a 50/50 state funded project. Total project funding is captured in the split budget summary slide.

## Slide 15: Orange Coast College Chemistry
Current Phase: In Construction Architect: tBP Architecture Contractor: Multiple Prime
Construction Manager: C.W. Driver
Scope: The Chemistry Building will replace the existing facility to result in academic spaces that are more efficient and productive, safer, and more technologically relevant for today’s teaching/ learning environment while also providing additional space needed for the growing Chemistry program.

## Slide 16
Orange Coast College
Chemistry

## Slide 17: Orange Coast College Chemistry
BIANNUAL REPORT: 4/1/24 – 9/30/24
Page 17
 | Budget | Biannual Expenses | Total Expended | Balance Remaining
Construction | $19,132,027 | $11,441,781 | $18,687,088 | $444,939
Soft Cost | $3,930,650 | $773,320 | $3,408,667 | $521,983
FFE/IT | $892,287 | $308,743 | $542,191 | $350,096
Contingency | $338,589 |  |  | $338,589
TOTAL | $24,293,553 | $12,523,844 | $22,637,946 | $1,655,607
 | Start
Design | January 2021
Plan Review | August 2021
Bidding | July 2022
Construction | October 2022
Project Completion | September 2024
Closeout | December 2024
BUDGET
SCHEDULE
Status Update: Building construction complete. Site landscaping and concrete work ongoing.
*Chemistry Project is a 50/50 state funded project. Negative balance is a result of Measure M originally absorbing all expenses, 50% of which will be reimbursed by State Proposition 51 funds.

## Slide 18
$17,145,010
Total Biannual Expenses
$618,190,645
Total Expenses From Inception
96.90%
Percentage of Project Funds Expended